## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 3580
|  | Actual: | 4015
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/O | Other | ALL | Student | Attend lecture |  | 2026-01-26 10:40 | 2026-01-26 12:30 | Completed | 2 | 1.83 | 0 | 0 | L01 – Introduction, S01 – The subject
2 | T0002/O | Other | ALL | Student | Attend lecture | T0001/O | 2026-01-29 08:30 | 2026-01-29 10:40 | Completed | 2 | 2.17 | 0 | 0 | L01 – Introduction, S02 – Working together
3 | T0003/O | Other | ALL | Student | Attend lecture | T0002/O | 2026-02-02 10:40 | 2026-02-02 12:30 | Completed | 2 | 1.83 | 0 | 0 | L01 – Introduction, S03 – Getting started
4 | T0004/O | Other | ALL | Student | Attend lecture | T0003/O | 2026-02-05 08:30 | 2026-02-05 10:40 | Completed | 2 | 2.17 | 0 | 0 | L01 – Introduction, S04 – The framework
5 | T0005/O | Other | ALL | Student | Attend lecture | T0004/O | 2026-02-09 10:40 | 2026-02-09 12:30 | Completed | 2 | 1.83 | 0 | 0 | Follow up
6 | T0006/O | Other | ALL | Student | Attend lecture | T0005/O | 2026-02-12 08:30 | 2026-02-12 10:40 | Completed | 2 | 2.17 | 0 | 0 | L02 – The data model, S01 – Models and queries
7 | T0007/O | Other | ALL | Student | Attend lecture | T0006/O | 2026-02-16 10:40 | 2026-02-16 12:30 | Completed | 2 | 1.83 | 0 | 0 | Follow up
8 | T0008/O | Other | ALL | Student | Attend lecture | T0007/O | 2026-02-19 08:30 | 2026-02-19 10:40 | Completed | 2 | 2.17 | 0 | 0 | L02 – The data model, S02 – Validation and population
9 | T0009/O | Other | ALL | Student | Attend lecture | T0008/O | 2026-02-23 10:40 | 2026-02-23 12:30 | Completed | 2 | 1.83 | 0 | 0 | Follow up
10 | T0010/O | Other | ALL | Student | Attend lecture | T0009/O | 2026-02-26 08:30 | 2026-02-26 10:40 | Completed | 2 | 2.17 | 0 | 0 | L02 – The data model, S03 – Advanced topics
11 | T0011/O | Other | ALL | Student | Attend lecture | T0010/O | 2026-03-02 10:40 | 2026-03-02 12:30 | Completed | 2 | 1.83 | 0 | 0 | Follow up
12 | T0012/O | Other | ALL | Student | Attend lecture | T0011/O | 2026-03-05 08:30 | 2026-03-05 10:40 | Completed | 2 | 2.17 | 0 | 0 | L03 – Implementing features, S01 – Display features
13 | T0013/O | Other | ALL | Student | Attend lecture | T0012/O | 2026-03-09 10:40 | 2026-03-09 12:30 | Completed | 2 | 1.83 | 0 | 0 | Follow up
14 | T0014/O | Other | ALL | Student | Attend lecture | T0013/O | 2026-03-12 08:30 | 2026-03-12 10:40 | Completed | 2 | 2.17 | 0 | 0 | L03 – Implementing features, S02 – Edition features
15 | T0015/O | Other | ALL | Student | Attend lecture | T0014/O | 2026-03-16 10:40 | 2026-03-16 12:30 | Completed | 2 | 1.83 | 0 | 0 | Follow up
16 | T0016/O | Other | ALL | Student | Attend lecture | T0015/O | 2026-03-19 08:30 | 2026-03-19 10:40 | Completed | 2 | 2.17 | 0 | 0 | L03 – Implementing features, S03 – Advanced topics
17 | T0017/O | Other | ALL | Student | Attend lecture | T0016/O | 2026-03-23 10:40 | 2026-03-23 12:30 | Planned |  |  |  |  | Assessments
18 | T0018/O | Other | ALL | Student | Attend lecture | T0017/O | 2026-03-26 08:30 | 2026-03-26 10:40 | Planned |  |  |  |  | Assessments
19 | T0019/M | Management | Student 1 | Manager | Make plans |  | 2026-01-26 15:00 | 2026-01-26 19:30 | Completed | 4 | 4.5 | 200 | 225 | Prepare the chartering report and the project planning document.
20 | T0020/M | Management | Student 1 | Manager | Initialise repository | T0019/M | 2026-01-28 16:00 | 2026-01-28 19:00 | Completed | 3 | 3 | 150 | 150 | Initialise the workgroup repository at GitHub.
21 | T0021/D | Development | Student 1 | Developer | Customise the starter | T0020/M | 2026-01-30 15:00 | 2026-01-30 19:30 | Completed | 4 | 4.5 | 100 | 112.5 | Instantiate the starter project "Hello-World" as "Acme-Starters-C".
22 | T0022/D | Development | Student 2 | Developer | Implement feature |  | 2026-01-29 15:00 | 2026-01-29 20:30 | Completed | 5 | 5.5 | 125 | 137.5 | Implement the constraints sketched in file “Model-CG.ufx” (Part 1).
23 | T0023/D | Development | Student 3 | Developer | Implement feature |  | 2026-02-02 15:00 | 2026-02-02 20:30 | Completed | 5 | 5.5 | 125 | 137.5 | Implement the constraints sketched in file “Model-CG.ufx” (Part 2).
24 | T0024/D | Development | Student 4 | Developer | Implement feature |  | 2026-02-03 15:00 | 2026-02-03 20:30 | Completed | 5 | 5.5 | 125 | 137.5 | Implement the constraints sketched in file “Model-CG.ufx” (Part 3).
25 | T0025/D | Development | Student 5 | Developer | Customise the starter |  | 2026-02-04 15:00 | 2026-02-04 19:00 | Completed | 4 | 4 | 100 | 100 | Design the corporate identity: colours, banners, and logos.
26 | T0026/QA/ | QA | Student 5 | Tester | Test performance formally | T0025/D | 2026-02-06 15:30 | 2026-02-06 18:00 | Completed | 2 | 2.5 | 60 | 75 | Create two administrator accounts (administrator1/2) and verify access.
27 | T0027/D | Development | Student 1 | Developer | Implement feature | T0021/D | 2026-02-04 15:00 | 2026-02-04 22:00 | Completed | 6 | 7 | 150 | 175 | Implement information requirements for Inventions and Parts (Model-C01.uxf).
28 | T0028/D | Development | Student 1 | Developer | Implement feature | T0027/D | 2026-02-09 15:00 | 2026-02-09 20:30 | Completed | 5 | 5.5 | 125 | 137.5 | List and display published Inventions, navigate to their Parts and see the Inventor profile.
29 | T0029/D | Development | Student 1 | Developer | Implement feature | T0028/D | 2026-02-11 16:00 | 2026-02-11 18:00 | Completed | 2 | 2 | 50 | 50 | Acquire the role "inventor" as long as the principal does not have that role yet.
30 | T0030/D | Development | Student 1 | Developer | Implement feature | T0029/D | 2026-02-13 15:30 | 2026-02-13 19:00 | Completed | 3 | 3.5 | 75 | 87.5 | Update the corresponding "inventor" role profile.
31 | T0031/D | Development | Student 1 | Developer | Implement feature | T0030/D | 2026-02-18 15:00 | 2026-02-18 23:00 | Completed | 7 | 8 | 175 | 200 | Manage (CRUD) his/her Inventions and their corresponding Parts.
32 | T0032/D | Development | Student 1 | Developer | Implement feature | T0031/D | 2026-02-23 15:30 | 2026-02-23 20:00 | Completed | 4 | 4.5 | 100 | 112.5 | Publish an Invention, which prevents it and its Parts from being updated or deleted.
33 | T0033/D | Development | Student 1 | Developer | Implement feature | T0032/D | 2026-03-04 15:00 | 2026-03-04 19:30 | Completed | 4 | 4.5 | 100 | 112.5 | Internationalise the UI and data (Boolean, money, dates) to EN/ES for the Inventor module.
34 | T0034/QA/ | QA | Student 1 | Tester | Test feature formally | T0033/D | 2026-03-10 15:30 | 2026-03-10 19:00 | Completed | 3 | 3.5 | 90 | 105 | Produce sample data for 3 Inventors (inventor1/2/3) and their associated data.
35 | T0035/D | Development | Student 2 | Developer | Implement feature | T0022/D | 2026-02-12 15:30 | 2026-02-12 22:30 | Completed | 6 | 7 | 150 | 175 | Implement information requirements for Campaigns and Milestones (Model-C02.uxf).
36 | T0036/D | Development | Student 2 | Developer | Implement feature | T0035/D | 2026-02-17 15:00 | 2026-02-17 20:30 | Completed | 5 | 5.5 | 125 | 137.5 | List and display published Campaigns, navigate to Milestones and see the Spokesperson profile.
37 | T0037/D | Development | Student 2 | Developer | Implement feature | T0036/D | 2026-02-19 15:30 | 2026-02-19 17:30 | Completed | 2 | 2 | 50 | 50 | Acquire the role "spokesperson" as long as the principal does not have that role yet.
38 | T0038/D | Development | Student 2 | Developer | Implement feature | T0037/D | 2026-02-24 15:30 | 2026-02-24 19:00 | Completed | 3 | 3.5 | 75 | 87.5 | Update the corresponding "spokesperson" role profile.
39 | T0039/D | Development | Student 2 | Developer | Implement feature | T0038/D | 2026-02-26 15:00 | 2026-02-26 23:00 | Completed | 7 | 8 | 175 | 200 | Manage (CRUD) his/her Campaigns and their corresponding Milestones.
40 | T0040/D | Development | Student 2 | Developer | Implement feature | T0039/D | 2026-03-03 15:30 | 2026-03-03 20:00 | Completed | 4 | 4.5 | 100 | 112.5 | Publish a Campaign, which prevents it and its Milestones from being updated or deleted.
41 | T0041/D | Development | Student 2 | Developer | Implement feature | T0040/D | 2026-03-05 15:00 | 2026-03-05 19:30 | Completed | 4 | 4.5 | 100 | 112.5 | Internationalise the UI and data (Boolean, money, dates) to EN/ES for the Spokesperson module.
42 | T0042/QA/ | QA | Student 2 | Tester | Implement feature | T0041/D | 2026-03-10 15:30 | 2026-03-10 19:00 | Completed | 3 | 3.5 | 90 | 105 | Produce sample data for 3 Spokespersons (spokesperson1/2/3).
43 | T0043/D | Development | Student 3 | Developer | Implement feature | T0023/D | 2026-02-05 15:00 | 2026-02-05 22:00 | Completed | 6 | 7 | 150 | 175 | Implement information requirements for Strategies and Tactics (Model-C03.uxf).
44 | T0044/D | Development | Student 3 | Developer | Implement feature | T0043/D | 2026-02-17 15:00 | 2026-02-17 20:30 | Completed | 5 | 5.5 | 125 | 137.5 | List and display published Strategies, navigate to Tactics and see the Fundraiser profile.
45 | T0045/D | Development | Student 3 | Developer | Implement feature | T0044/D | 2026-02-26 15:30 | 2026-02-26 17:30 | Completed | 2 | 2 | 50 | 50 | Acquire the role "fundraiser" as long as the principal does not have that role yet.
46 | T0046/D | Development | Student 3 | Developer | Implement feature | T0045/D | 2026-03-03 15:30 | 2026-03-03 19:00 | Completed | 3 | 3.5 | 75 | 87.5 | Update the corresponding "fundraiser" role profile.
47 | T0047/D | Development | Student 3 | Developer | Implement feature | T0046/D | 2026-03-05 15:00 | 2026-03-05 23:00 | Completed | 7 | 8 | 175 | 200 | Manage his/her Strategies and their corresponding Tactics (create, update, or delete).
48 | T0048/D | Development | Student 3 | Developer | Implement feature | T0047/D | 2026-03-10 15:30 | 2026-03-10 20:00 | Completed | 4 | 4.5 | 100 | 112.5 | Publish a Strategy, which prevents it and its Tactics from being updated or deleted.
49 | T0049/D | Development | Student 3 | Developer | Implement feature | T0048/D | 2026-03-12 15:00 | 2026-03-12 19:30 | Completed | 4 | 4.5 | 100 | 112.5 | Internationalise UI and data (Boolean, money, dates) to EN/ES for the Fundraiser module.
50 | T0050/QA/ | QA | Student 3 | Tester | Test feature formally | T0049/D | 2026-03-17 15:30 | 2026-03-17 19:00 | Completed | 3 | 3.5 | 90 | 105 | Produce sample data for 3 Fundraisers (fundraiser1/2/3) and their associated data.
51 | T0051/D | Development | Student 4 | Developer | Implement feature | T0024/D | 2026-02-06 15:00 | 2026-02-06 22:00 | Planned | 0 | 0 | 0 | 0 | Implement information requirements for Sponsorships and Donations (Model-C04.uxf).
52 | T0052/D | Development | Student 4 | Developer | Implement feature | T0051/D | 2026-02-18 15:00 | 2026-02-18 20:30 | Planned | 0 | 0 | 0 | 0 | List and display published Sponsorships, navigate to Donations and see the Sponsor profile.
53 | T0053/D | Development | Student 4 | Developer | Implement feature | T0052/D | 2026-02-20 15:30 | 2026-02-20 17:30 | Planned | 0 | 0 | 0 | 0 | Acquire the role "sponsor" as long as the principal does not have that role yet.
54 | T0054/D | Development | Student 4 | Developer | Implement feature | T0053/D | 2026-02-25 15:30 | 2026-02-25 19:00 | Planned | 0 | 0 | 0 | 0 | Update the corresponding "sponsor" role profile.
55 | T0055/D | Development | Student 4 | Developer | Implement feature | T0054/D | 2026-02-27 15:00 | 2026-02-27 23:00 | Planned | 0 | 0 | 0 | 0 | Manage his/her Sponsorships and their corresponding Donations (create, update, or delete).
56 | T0056/D | Development | Student 4 | Developer | Implement feature | T0055/D | 2026-03-04 15:30 | 2026-03-04 20:00 | Planned | 0 | 0 | 0 | 0 | Publish a Sponsorship, which prevents it and its Donations from being updated or deleted.
57 | T0057/D | Development | Student 4 | Developer | Implement feature | T0056/D | 2026-03-06 15:00 | 2026-03-06 19:30 | Planned | 0 | 0 | 0 | 0 | Internationalise UI and data (Boolean, money, dates) to EN/ES for the Sponsor module.
58 | T0058/QA/ | QA | Student 4 | Tester | Test feature formally | T0057/D | 2026-03-11 15:30 | 2026-03-11 19:00 | Planned | 0 | 0 | 0 | 0 | Produce sample data for 3 Sponsors (sponsor1/2/3) and their associated data.
59 | T0059/D | Development | Student 5 | Developer | Implement feature | T0026/QA/ | 2026-02-09 15:00 | 2026-02-09 22:00 | Planned | 0 | 0 | 0 | 0 | Implement information requirements for Audit Reports and Sections (Model-C05.uxf).
60 | T0060/D | Development | Student 5 | Developer | Implement feature | T0059/D | 2026-02-12 15:30 | 2026-02-12 21:00 | Planned | 0 | 0 | 0 | 0 | List and display published Audit Reports, navigate to Sections and see the Auditor profile.
61 | T0061/D | Development | Student 5 | Developer | Implement feature | T0060/D | 2026-02-24 15:30 | 2026-02-24 17:30 | Planned | 0 | 0 | 0 | 0 | Acquire the role "auditor" as long as the principal does not have that role yet.
62 | T0062/D | Development | Student 5 | Developer | Implement feature | T0061/D | 2026-03-02 15:30 | 2026-03-02 19:00 | Planned | 0 | 0 | 0 | 0 | Update the corresponding "auditor" role profile.
63 | T0063/D | Development | Student 5 | Developer | Implement feature | T0062/D | 2026-03-05 15:00 | 2026-03-05 23:00 | Planned | 0 | 0 | 0 | 0 | Manage his/her Audit Reports and their corresponding Audit Sections.
64 | T0064/D | Development | Student 5 | Developer | Implement feature | T0063/D | 2026-03-09 15:30 | 2026-03-09 20:00 | Planned | 0 | 0 | 0 | 0 | Publish an Audit Report, which prevents it and its Sections from being updated or deleted.
65 | T0065/D | Development | Student 5 | Developer | Implement feature | T0064/D | 2026-03-12 15:00 | 2026-03-12 19:30 | Planned | 0 | 0 | 0 | 0 | Internationalise UI and data (Boolean, money, dates) to EN/ES for the Auditor module.
66 | T0066/QA/ | QA | Student 5 | Tester | Test feature formally | T0065/D | 2026-03-18 15:30 | 2026-03-18 19:00 | Planned | 0 | 0 | 0 | 0 | Produce sample data for 3 Auditors (auditor1/2/3) and their associated data.
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/O | Other | ALL | Student | Attend lecture |  | 2026-04-06 10:40 | 2026-04-06 12:30 | Planned |  |  |  |  | L04 – Formal testing, S01 – Functional testing
2 | T0002/O | Other | ALL | Student | Attend lecture | T0001/O | 2026-04-09 08:30 | 2026-04-09 10:40 | Planned |  |  |  |  | L04 – Formal testing, S02 – Performance testing
3 | T0003/O | Other | ALL | Student | Attend lecture | T0002/O | 2026-04-13 10:40 | 2026-04-13 12:30 | Planned |  |  |  |  | Follow up
4 | T0004/O | Other | ALL | Student | Attend lecture | T0003/O | 2026-04-16 08:30 | 2026-04-16 10:40 | Planned |  |  |  |  | L04 – Formal testing, S03 – Advanced topics
5 | T0005/O | Other | ALL | Student | Attend lecture | T0004/O | 2026-04-20 10:40 | 2026-04-20 12:30 | Planned |  |  |  |  | Follow up
6 | T0006/O | Other | ALL | Student | Attend lecture | T0005/O | 2026-04-27 10:40 | 2026-04-27 12:30 | Planned |  |  |  |  | Follow up
7 | T0007/O | Other | ALL | Student | Attend lecture | T0006/O | 2026-04-30 08:30 | 2026-04-30 10:40 | Planned |  |  |  |  | Assessments
8 | T0008/O | Other | ALL | Student | Attend lecture | T0007/O | 2026-05-04 10:40 | 2026-05-04 12:30 | Planned |  |  |  |  | Assessments
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/O | Other | ALL | Student | Attend lecture |  | 2026-05-07 08:30 | 2026-05-07 10:40 | Planned |  |  |  |  | L05 – Miscellaneous topics, S01 – Workshop
2 | T0002/O | Other | ALL | Student | Attend lecture | T0001/O | 2026-05-11 10:40 | 2026-05-11 12:30 | Planned |  |  |  |  | Workshop Presentations
3 | T0003/O | Other | ALL | Student | Attend lecture | T0002/O | 2026-05-14 08:30 | 2026-05-14 10:40 | Planned |  |  |  |  | L05 – Miscellaneous topics, S02 – Advanced topics
4 | T0004/O | Other | ALL | Student | Attend lecture | T0003/O | 2026-05-18 10:40 | 2026-05-18 12:30 | Planned |  |  |  |  | Assessments
5 | T0005/O | Other | ALL | Student | Attend lecture | T0004/O | 2026-05-21 08:30 | 2026-05-21 10:40 | Planned |  |  |  |  | Assessments
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O